## Planned_vs_Actual_Sprint
Planned | Actual | US ID | User Story | Dependency | Assignee | Status
S1 | S1 | US-001 | Create Login UI | No Dependency | Sujal | Completed
S1 | S1 | US-002 | Register User API | No Dependency | Sujal | Completed
S1 | S2 | US-003 | Login Authentication | US-001 | Sujal | Completed
S2 | S2 | US-004 | Add Product Feature | US-003 | Sujal | Completed
S2 | S2 | US-005 | Update/Delete Product | US-004 | Sujal | Completed
S3 | S3 | US-006 | Inventory Dashboard | US-005 | Sujal | Completed
S3 | S3 | US-007 | Reports & Analytics | US-006 | Sujal | Completed
S4 | S4 | US-008 | Testing & Bug Fixing | All | Sujal | Completed
S4 | S4 | US-009 | Deployment | US-008 | Sujal | Pending

## Sprint_1_Backlog
US ID | Task Description | Priority | Status
US-001 | Design Login Page UI | High | Completed
US-001 | Add Input Validation | Medium | Completed
US-002 | Create Register API | High | Completed
US-003 | Implement Login API | High | In Progress

## Sprint_2_Backlog
US ID | Task Description | Priority | Status
US-004 | Create Add Product Form | High | Pending
US-004 | Backend API for Product | High | Pending
US-005 | Update Product Feature | Medium | Pending
US-005 | Delete Product Feature | Medium | Pending

## Sprint_3_Backlog
US ID | Task Description | Priority | Status
US-006 | Dashboard UI | High | Pending
US-006 | Fetch Inventory Data | High | Pending
US-007 | Generate Reports | Medium | Pending
US-007 | Charts Integration | Low | Pending

## Sprint_4_Backlog
US ID | Task Description | Priority | Status
US-008 | Testing All Features | High | Pending
US-008 | Fix Bugs | High | Pending
US-009 | Deploy Backend | Medium | Pending
US-009 | Deploy Frontend | Medium | Pending